Centers for Disease Control and Prevention Limited-Scale Community Reception Center Drill

Appendix A: Improvement Plan Matrix

# APPENDIX A: IMPROVEMENT PLAN MATRIX

This Improvement Plan has been developed specifically for the Centers for Disease Contol and Florida Department of Health  Limited-Scale Drill Functional Exercise conducted on July 12, 2011.

Table 6—Improvement Plan Matrix

| Capability | Recommendation | Corrective Action Description | Capability Element | Primary Agency and Point of Contact | Start Date | Completion Date |
| --- | --- | --- | --- | --- | --- | --- |
| General | Ensure that all Community Reception Center (CRC) response personnel have a basic knowledge of all stations within CRC. | Provide cross-training for all CRC response personnel | Training | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Consult the Regional Epidemiological Strike Team Coordinator when making assignments for the Epidemiological Strike Team. | Before exercises or as needed, consult the Regional Epidemiological Strike Team Coordinator to determine available team members and level of asset typing. | Planning | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Exercise treatment recommendations indicated for radiological events. | Practice the treatment recommendations made during the exercise. | Exercise | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Compile resource lists for packaging and shipping of biological specimens. | Obtain resource lists and materials appropriate for the packing and shipping of specimens (dry ice, etc.). | Planning | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | More consistency on completing forms—staff filling out forms should sign off on the completed sections | Provide participants with clear instructions on filling out forms and encourage them to sign off on the sections they complete. | Planning | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Further training on ICS structure and chain of command within a CRC. | Train/practice Community Reception Center ICS structure and chain of command procedures. Look at improving staffing methods for span of control and surge influx. | Planning/ Training/ Exercise | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Have more staff at registration and discharge stations to avoid lengthy wait times and increased anxiety. | Look at staffing increases for registration and discharge stations to reduce choke points. | Planning | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Have closer monitoring of persons and equipment that move between the clean and contaminated control zone without don/doff of personal protective equipment. | Review CRC procedures for monitoring the divide between clean and contaminated control zones. Consider security personnel. | Planning | TBD | TBD | TBD |
| Epidemiological Surveillance and Investigation | Ensure proper units from the radiation monitoring equipment are entered into the computer program. | Provide a very knowledgeable person in radiation dose rates be stationed at dose assessment station. | Training | TBD | TBD | TBD |
| Environmental Health | Have a numbering system for wait area at registration and discharge. | Examine different ways to track patients at registration and discharge stations. | Planning | TBD | TBD | TBD |
| Environmental Health | Provide better physical separation between victims being scanned for internal contamination and other victims waiting to be scanned. | Analyze separation methods for victims being scanned and waiting to be scanned to help eliminate false reporting. | Planning | TBD | TBD | TBD |
| Environmental Health | Better integrate the internal functions of dose assessment | Train on the functions and processes for dose assessment | Planning/ Training | TBD | TBD | TBD |
| Public Health Laboratory Testing (urine sample shipping | Use of lab specimen’s barcode and patient tracking barcode created the need for a cross-referencing system. | Integrate different barcodes into one system for more efficient and faster tracking | Equipment | TBD | TBD | TBD |
| On-Site Incident Management | Provide Incident Command System (ICS) Toolkit on jump drives to eliminate different formats of ICS forms. | Obtain multiple jump drives and load them with the ICS Toolkit. | Equipment | Florida Regional Domestic Security Task Force (RDSTF) Region 5 Incident Management Training (IMT) | 8/1/11 | 8/1/12 |
| On-Site Incident Management | Have one laptop and printer assigned to the IMT at all times. | Obtain a designated IMT laptop and printer. | Equipment | Florida RDSTF Region 5 IMT | 8/1/11 | 8/1/12 |
| On-Site Incident Management | Market for more finance/administrative section chiefs. | Advertise finance and administrative IMT positions to appropriate personnel | Planning/ Training | Florida RDSTF Region 5 IMT | 8/1/11 | Ongoing |
| On-Site Incident Management | Regulate requisition requests. | Look at methods to standardize requisition requests. | Planning | Florida RDSTF Region 5 IMT | 8/1/11 | 8/1/12 |
| On-Site Incident Management | Investigate ways to correct confusion between multiple types of e-mail accounts and firewalls from various organizations participating on the IMT. | Google docs and possibly Google position-based accounts would eliminate confusion of various types of e-mails and firewalls from various organizations. | Planning/ Equipment | Florida RDSTF Region 5 IMT | 8/1/11 | 8/1/12 |
| Disaster Behavioral Health | Revise triage methods. | Blue—no assessment needed; provide coping information. Green—mini-assessment and support plan. Orange—mental health assessment and referrals. User markers (only mark green and orange). | Planning/ Training | Florida Crisis Consortium (FCC) | 8/1/11 | 9/1/11 |
| Disaster Behavioral Health | Obstain more interpreters for non-English speakers. | Recruit additional bilingual team members. | Planning | FCC | 8/1/11 | Ongoing |
| Disaster Behavioral Health | Revise staffing matrix. | Identify staffing needed (including backup team leader to build in breaks for team members). | Training | FCC | 8/1/11 | 9/30/11 |
| Disaster Behavioral Health | Develop better communication between clean side and contaminated side | Designate lead on each side and provide radio. | Planning/ Training | FCC | 8/1/11 | 9/30/11 |
| Disaster Behavioral Health | Revisit fitness-for-duty guidelines. | Revise guidelines and communicate to team members . | Planning/ Training | FCC | 9/1/11 | 10/31/11 |