YEAR 1 OBJECTIVES IMPLEMENTATION PLAN

|  |
| --- |
| **Date Completed: 07/13/2022** |

|  |  |
| --- | --- |
| **SUBJECT:** Rare Disease Advisory Council Year 1 Objectives | **SUBCOMMITTEE RESPONSIBLE FOR IMPLEMENTATION:** Health Care Providers |

| **RECOMMENDATIONS** | **OBJECTIVES** | **ACTION STEPS TO IMPLEMENT OBJECTIVE** | **ACTION STEP DUE**  **DATE** | **PERSON(S) RESPONSIBLE** | **COORDINATION WITH** | **STATUS/NOTES** |
| --- | --- | --- | --- | --- | --- | --- |
| Recommendation 1: Promote education on rare diseases to health care providers. | Objective 1.1: Identify existing educational resources, including continuing education courses, for health care providers on various topics related to rare diseases. | * Identify National/State Continuing Education providers. * Identify Rare Disease Organizations with Continuing Education Resources | August 10, 2022 | Zana Dupee  Anita Davis | N/A | 7/13/22: Zana and Anita Davis will be researching available CE providers (national/state/and RD organizations). |
| Objective 1.2: Identify educational resources on patient-centered care for health care providers. | * Identify National/State partners who have completed research on patient centered care. | September 14, 2022 | Zana Dupee  Anita Davis | N/A |  |
| Objective 1.3: Identify educational resources on holistic health care practices for health care providers. | * Identify National/State providers who currently have holistic health care practices in place in their practice. | TBD | Jessica O’Reilly | Mayo Clinic |  |
| Objective 1.4: Centralize educational resources on a publicly available website. | * Continuing research on other state RDAC webpages for publicly posting identified resources on FL RDAC webpage. * Reach out to FDOH web development team to plan for public RDAC website. | September 14, 2022 | Casey Omeke | FDOH Web Developers Team |  |
| Recommendation 2: Promote advancements in the process of achieving a diagnosis for rare diseases. | Objective 1.1: Identify screening tools for health care providers on rare diseases. | * Identifying National/State screening tools for health care providers. | September 14, 2022 | Rebekah Dorr  Zana Dupee  Anita Davis |  |  |
| Recommendation 3: Promote advancements in the process of achieving treatments for rare diseases. | Objective 1.1: Identify current medical practices and specialists who accept both pediatric and adult individuals with rare diseases. |  |  |  |  |  |
| Objective 1.2: Identify barriers and challenges to medical practices and specialists accepting both pediatric and adult individuals with rare diseases. |  |  |  |  |  |
| Objective 1.3: Develop a list of resources for individuals with rare diseases on how to self-advocate during interactions with health care providers. |  |  |  |  |  |